## Sheet1
II- Project | Indrumarea in cariera
User Story Map
user | high school student
goal | search for a faculty which suits me better
| User Activity | Sign Up/Sign In |  |  |  | Choose a test | Resolve the test |  |  | Read the results | Choose between recomanded faculties
| User Steps | Enter the Home Page | Create New Account | Authentificate | Enter in the User Page | Start test 1 | Answer the Questions 1 | Start test 2 | Answer the Question 2 | Read the user's profile | Choose one facultity from the list | Select an Option ( one faculty) | Save to Favorites | Compare between two options
| User Tasks | Read the description of the application | Insert Your Email, Password and Password Comfirmation | Insert Email and Password | Choose to Make the Test | Read Infromation about Test no 1 | Answer the Questions | Read Infromation about Test no 2 | Answer the Questions | Read the Results of the Test no 1 | Order By Country | Read about the faculty | Select Save to my Favorites | Select Compate (first option)
|  | Choose Create New Account(Sign Up) /Authentificate(Sign In) | Comply with the General Data Protection Regulation(GDPR) |  |  | Choose Start Test | Select Finish Test | Choose Start Test | Select Finish Test | Read the Results of the Test no 2 | Order by the number of publications | Read about the cost of live, information about the city | Enter in the Favorites List | Select Compate (second option)
|  |  | Google CAPCHA | [7 empty] | Order by the ……. (further criterion) |  |  | View Comparison
Select an Option
Demo 1
|  | Page Design:Home Page | Create User DataBase |  |  | Choose test format 1 |  |  |  |  | Choose University information format
Demo 2
|  |  | Design Page: New Account |  |  | Design Page: Test 1 | Create the Database of the Question 1 | Choose test format 2 |  | Algoritm: Interpret the results | Create Database: University's informations
Demo 3
|  |  | Algorithm: New Account | Design Page: Login |  |  | Algorithm: Test 1 | Design Page: Test 2 | Create the Database of the Question 2 |  |  | Design Page: Faculty Profile
Demo 4
|  |  | Test: Sign In | Algorithm: Sign In | Design Page: User Home Page |  |  |  | Algorithm: Result Test 2 | Design Page: Results Test | Algorithm:Sort results |  | Design Page: Favorites List
Demo 5
|  |  |  | Test: New Account | Algorithm: User Home Page | [8 empty] | Design Page: Compare
Demo 6